## Sheet1
Task | Start Date | End Date | Start on Day | Duration
Create Random Map Generator | 2023-03-20 | 2023-03-27 | 0 | 7
Add all the tokens | 2023-03-20 | 2023-03-27 | 7 | 7
Have 1 Player Token Manually interact with tiles | 2023-03-27 | 2023-04-03 | 14 | 7
Have 1 Player Manually solve token with tiles | 2023-03-27 | 2023-04-03 | 21 | 7
Have 1 Player Auto solve token with A*star in Known Map | 2023-03-27 | 2023-04-03 | 28 | 7
Have 1 Player Pick up >6 one color Tokens, Grab one color Speical then Exit in known map | 2023-03-27 | 2023-04-03 | 35 | 7
Repeat previous Step with two colors | 2023-04-03 | 2023-04-10 | 42 | 7
Repeat previous Step with three colors and the Fire of Eidolon | 2023-04-03 | 2023-04-10 | 49 | 7
Investigate other types of searches | 2023-04-03 | 2023-04-10 | 56 | 7
Repeat previous goals with color specializations | 2023-04-10 | 2023-04-25 | 63 | 15
Develop map that is generated with player | 2023-04-10 | 2023-04-25 | 78 | 15
Repeat previous goals with unknown map specializations | 2023-04-10 | 2023-04-25 | 93 | 15
Repeat all previous steps with 2-6 players | 2023-04-10 | 2023-04-25 | 108 | 15
Develop map and player actions with cultists | Stretch | Stretch | 123 | 0
Repeat all previous steps with cultists | Stretch | Stretch | 123 | 0
Repeat all previous steps with Hero Abilities | Stretch | Stretch | 123 | 0
Repeat all steps with the different game levels | Stretch | Stretch | 123 | 0
last day April 25, 2023